## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Project intitialization & empty grid generation | 1 | 2023-03-30 | Set up the repository for the project. Laid out the code foundations. Enums for cell and wall types. ICell and IGridGenerator interfaces so I can support different types of cells and grids. (Planning to implement a grid with hexagonal cells). SquareCell and SquareGridGenerator to create a basic square grid. Finally a MazeManager to tie everything together. I plan to use the Depth First Search algorithm to generate the maze. That's why the cell prefab is set up with walls (the algorithm removes walls between neighbouring cells to create a path).
Depth First Search implementation | 1.5 | 2023-03-30 | Implemented the Depth First Search algorith in the MazeManager, but it will be later extracted to a separate class called MazeGenerator to adhere to SOLID principles. Added a IWallRemover interface and a SqareWallRemover implementation of it. The SqareCell script implements the ICell interface and it is attatched to the SquareCell prefab. The GetRandomUnvisitedNeighbour method first uses a helper method to cache the unvisited neighbours in a list (only happens once). Then uses a nested helper method to remove any visited neighours from the list. If the list becomes empty it returns null. If list is not empty it returns a random element from it.
UI implementation | 2.5 | 2023-03-31 | Implemented a simple UI in which the user can input the width and the height of the maze and also choose to animate the generation. The UI is responsive and looks good in the specified resolutions. Only in extreme aspect ratios we see some overlap, but everything is still functional. Added a UIManager class to handle the input from the UI. Moved the maze generation to a MazeGenerator class. The maze can be regenerated from the UI. Next step is to centre the maze in the camera so it is fully visible.
Maze Alignment | 1 | 2023-04-03 | Added a small class called MazeAligner. It has a method that centres the maze on the screen by ajusting the position of the MazeHolder and the main camera's orthographic size. The calculations use the halves of the width and the height and a further subtraction of 0.5. Then the maze holder position uses the negative result of the calculations so the maze is always at the dead centre of the screen. To fit the entire maze on the screen the camera's size is set to the bigger of the two previously calculated halves to which an additional 1 is added so there's a margin. The calculations happen two nested helper methods: float CalculateHalf(float whole) and void SetCameraPosition() to improve code readability.
Hexagonal Cell Implementation | 2 | 2023-04-04 | Implemented a hexagonal cell. To make this posible I made a new HexCell prefab with a HexCell script that inherits from ICell. There's a new class HexCellWallRemover that inherits from IWallRemover. I will attempt to merge the two classes and use a dictionary to store the walls and get rid of the switch case. There's also a new class HexGridGenerator that inherits from IGridGenerator. A hex grid requires a more complex math than a square grid. Finally, I added a dropdown list in the UI that is populated from the Cell enum. When the value is changed it is recorded in the MazeManager, which subscribes and unsubscribes the respective gridGenerators from the events. | x
Aldous-Broder implementation | 1 | 2023-04-04 | To make the algorithm work I had to implement a GetRandomNeighbour() method for each type of cell. The algorithm stands in its own class AB_MazeGenerator. Both AB_MazeGenerator and DSF_MazeGenerator inherit from IMazeGenerator. In the MazeManager they are cached in a dictionary with the Algorithm enum as the key. There's a dropdown in the UI that is populated from the Algorithm enum. Every change is reflected in the Algorithm property of the MazeManager. | x
Final polishing and bug fixing | 3 | 2023-04-05 | Added summaries and regions to make the code more readable. Encountered a bug where if you switched algorithms before a maze had finished generating multiple coroutines (maze generating algorithms) were running on the same grid. It took me some time of trial and error to figure out the simple fix. Which is to stop all coroutines before generating a new maze and when doing an algorithm change. If I could I would have a senior developer for help after getting stuck and probably would have saved time.
Switching to a dictionary | 0.5 | 2023-04-05 | Discovered a bug just before submitting. Using doubled coordinates for the hex grid and storing it in a 2D array left half of the array empty. This broke the Aldous-Broder algorithm. Furthermore it is a waste of memory. Therefore, I stored the grid in a Dictionary. The coordinates of each cell are stored in a Vector2 which is used as the key for the dictionary. Lastly, I made sure the width is dobled when using hexagons to ensure a square looking grid.
Total amount of hours | 9.5